Assignment 3

CSG2344 - Project Methods and Professionalism

Jordan Farrow (10653054)

Andrii Lukaschuk (10691443)

Aaron Kalaji (10670705)

Harrison Stubbs (10652268)

19 October, 2025

Table of Contents

1. Introduction	4

2. Project Integration	4

2.1. Project Initiation & Set-Up	4

2.2. Technology Solution Development (Phase 1)	5

2.3. Technology Solution Development (Phase 2)	5

2.4. Application Deployment & Final Testing	5

2.5. Hand Over	6

3. Costs and Budgeting	6

3.1. Budget Allocation	7

3.2. Staff Costs	14

3.3. Hardware costs	14

3.4. Software Costs	15

3.5. Cloud Costs	15

3.6. Premises Costs	15

3.7. Transports Costs	15

3.8. Miscellaneous Costs	15

4. Assessment of Risk	15

4.1. Risk Register	16

4.2. Risk Matrix	28

4.3. Risk #32	28

4.4. Risk #36	29

4.5. Risk #74	29

4.6. Risk #104	30

4.7. Risk #114	30

5. Project Roles	30

5.1 Removalists	32

5.2. IT Technician	32

5.3. Janitor	32

5.4. Lead Accountant	32

5.5. Accountant	32

5.6. Field Technician	32

5.7. Quality Field Inspector	33

5.8. Lead Embedded System Engineer	33

5.9. Embedded System Engineer	33

5.10. Lead Vision Model Engineer	33

5.11. Vision Model Engineer	33

5.12. Lead Back-End Mobile Application Developer	33

5.13. Back-End Mobile Application Developer	34

5.14. Lead Front-End Mobile Application Developer	34

5.15. Front-End Mobile Application Developer	34

5.16. Lead Cyber Operator	34

5.17. DevOps	35

5.18. Lead Cloud Engineer	35

5.19. Cloud Engineer	35

5.20. Pentester	35

5.21. Quality Assurance Tester	35

5.22. Compliance Officer	35

5.23. Human Resources (HR)	35

5.24. Risk Officer	36

5.25. System Analyst	36

5.26. Lead Network Engineer	36

5.27. Network Engineer	36

6. Professionalism	36

6.1. Soft Skills	37

6.2. Hard Skills	39

6.3. Ethics	40

6.4. Government and Corporate Communications	40

# 1. Introduction

SSCI-Hooli has proposed a technology-driven solution for reducing road potholes through a public private partnership between public partner Western Australian (WA) Government and private partner SSCI-Hooli. SSCI-Hooli is tasked with producing automatic and civic reporting pothole detection applications to improve remediation efforts and awareness. The WA Government has provided $12 million in funding to meet the project deliverables and success criteria disclosed in the project charter.

This report discusses the integration of project roles for achieving tasks defined within the project timeline. In addition, the allocation of the $12 million budget is documented, with discussions on how it positively impacts the project. Following is an assessment of risks which can impact SSCI-Hooli’s success of meeting the project deliverables and success criteria. Finally, the various roles and their task delegations within the project are documented, with a final discussion on the project’s professionalism.

# 2. Project Integration

A variety of hardware and software will be integrated per team or business wide for fulfilling project deliverables.

For application and vision model development, the Python and Flutter programming languages will be used within Visual Studio Code environments, utilising CVAT for dataset processing and Flutterflow for prototyping. The system analysis documentation to be followed will be produced using both Office365 and Lucidchart. Source code will be stored within a GitHub repository, with MS Teams file storage available for non-development employees.

Completed source code will be integrated into the configured cloud infrastructure, using the back-end of each application to communicate with the MongoDB cloud database for pothole data storage and the EC2 instances which house and power the cloud-driven applications.

Jira and Notion will be integrated by all employees to track current tasks and deadlines, in addition to collaborating beyond MS Teams call and file storage functionality.

The Zed Boxes and stereo cameras will be integrated into a single Python program providing video feed and computing ability to the machine vision model. Upon reaching a bus port, pothole data will be sent to the EC2 cloud servers for further processing.

## 2.1. Project Initiation & Set-Up

This phase involves the initial set-up of the premises and resources SSCI-Hooli requires; it begins with contacting the steering committee to ensure the project scope remains unchanged.

Between the 4 project managers the development contractors are to be procured, in addition to the hardware to be fitted within the 1,690 buses. A project manager will also schedule the hardware installations based on the bus schedule the Department of Transport provides.

To furnish the premises, removalists are contracted for 10 days, with IT technicians setting each laptop with the software required by employees.

## 2.2. Technology Solution Development (Phase 1)

Development begins with the machine vision, back and front-end teams. The machine vision team will integrate the CVAT data annotation application with the pothole-600 dataset for analysis and pre-processing. Next, the team will use the Python programming language within a visual studio code environment to create a prototype YOLOv5 pothole and early sign detection model. Following with 4 days of model testing to determine improvements to be made within phase 2.

The front-end team will begin development on the civic reporting app and web map, making changes with the system analysis documentation. The team leads will use the first 14 days of phase 1 to allow for brainstorming discussions for team alignment and to create prototypes using Flutterflow. From the prototypes, two teams each consisting of a team lead and 4 front-end developers will create the frame of the applications based on the prototypes.

The phase finishes with the vision model and application prototypes shown to the steering committee, demonstrating project progress.

Throughout the phase, the field technician team will be fitting 250 public transport buses with the physical technology required for automatic pothole detection.

## 2.3. Technology Solution Development (Phase 2)

Phase begins with a review of SSCI-Hooli’s compliance with ISO standards, laws, regulations and policies.

The front and back-end 10-man teams will separate into teams of 5 to continue developing the civic reporting app and web map, in addition to beginning the early pothole sign dashboard. The teams will continue using their respective branches of the GitHub repository, integrating Flutter to build upon the prototypes. After 20 development days, the team leads will offer their applications to quality assurance testers and stakeholders for feedback on user accessibility and friendliness. The feedback will then be used to adjust the applications.

The machine vision team will continue refining the parameters of the YOLOv5 model, taking into consideration the results of testing in phase 1.

The cloud engineering team will be introduced to integrate the current back-end source code with the EC2 cloud server instances and MongoDB Atlas database. It must be ensured that all pothole related data is sent for storage within the MongoDB Atlas database, with the EC2 server instances used to power the to-be cloud applications.

The cybersecurity team will also be introduced, hardening the digital security of SSCI-Hooli’s technology driven solution.

The phase ends with a technical demonstration of the applications to the steering committee.

## 2.4. Application Deployment & Final Testing

This phase involves the front-end, back-end and cloud infrastructure teams finalising the applications and ensuring the back-ends communicate efficiently with the cloud servers. The application will be trialled by stakeholders for 11 days, with 7 additional days allocated towards tuning the application. The machine vision team will have completed their vision model for automatic pothole detection, which is rolled out to current technology fitted buses.

Pentesters will analyse the security measures implemented within the prior phase, giving constructive feedback to the cybersecurity team which will then be acted upon.

Although fitting buses with the embedded system technology is within this phase, it occurs within the earlier phases, occurring shortly after the prior 250 buses are fitted.

## 2.5. Hand Over

Upon entering this phase, development for the technology driven solution is complete, with all source code, cloud infrastructure and documentation to be handed to the WA Government.

The steering committee will be provided a final demonstration to show project deliverables have been met, with strong early success in meeting all points of the success criteria.

The project closes with required employees receiving training for the applications, with the wide release of the civic reporting app and web map.

# 3. Costs and Budgeting

Project costs are categorised into staff, hardware, software, cloud, security, transport and miscellaneous categories.

Staff costs includes all employee contracts and additional expenditures to increase workplace satisfaction. It has been allocated $3,304,687.99 of the budget.

Hardware costs involves the physical technologies required to perform automatic pothole detection, source code development and supporting hardware required within the premises. It has been allocated $6,740,236.28 of the budget.

Software costs involve digital licenses and subscriptions required for SSCI-Hooli's daily workflows. It has been allocated $263,747.90 of the budget.

Cloud costs involve all cloud infrastructure SSCI-Hooli will rent and configure for pothole data storage and application powering. It has been allocated $64,367.95 of the budget.

Security costs involve physical and digital resources to secure the premises and systems from unauthorised entity access. It has been allocated $35,052.96 of the budget.

Premises costs involve the premises SSCI-Hooli will utilise, furniture and additional appliances employees may utilise. It has been allocated $119,229.98 of the budget.

Transportation costs involve resources allocated to tasks requiring travel away from the premises. It has been allocated $40,000 of the budget.

Miscellaneous costs involve resources unable to be categorised into the prior categories such as, the contingency reserve. It has been allocated $1,432,676.94 of the budget.

Within order; hardware, staff and software costs were prioritised in the budget allocation. Without allocating budget to the embedded systems, buses may not receive systems thus, not meeting project deliverables. Likewise, without early consideration of staff costs, the number of possible contracts achievable could decrease, reducing the ability to meet deadlines. The systems and software to be used by employees were then prioritised; without a computer system or relevant software, employees will be limited in the work possible. After allocations to hardware, staff and software were completed, cloud, premises, security, transportation and miscellaneous costs were delegated.

## 3.1. Budget Allocation

| Staff Costs |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Link | Item | Qty. |  |  | Cost per item | Total item costs |  |
| https://elitemovers.com.au/ | Removalist Contract | 1 |  |  | $100/hour | $5400 |  |
| https://www.seek.com.au/career-advice/role/information-technology-support-technician/salary | IT Technician Contract | 3 |  |  | $245/day | $68,355 |  |
| https://www.glassdoor.com.au/Salaries/janitor-salary-SRCH_KO0,7.htm | Janitor Contract | 2 |  |  | $250/day | $43,000 |  |
| https://www.glassdoor.com.au/Salaries/accounting-team-lead-salary-SRCH_KO0,20.htm | Lead Accountant contract | 1 |  |  | $500/day | $49,500 |  |
| https://www.seek.com.au/career-advice/role/accountant/salary | Accountant contract | 2 |  |  | $245/day | $48,510 |  |
| https://www.seek.com.au/career-advice/role/field-service-technician/salary | Field Technician contract | 3 |  |  | $270.57/day | $54,384.57 |  |
| https://www.glassdoor.com.au/Salaries/quality-inspector-salary-SRCH_KO0,17.htm | Quality Field Inspector contract | 1 |  |  | $265.57/day | $17,793.19 |  |
| https://www.glassdoor.com.au/Salaries/lead-systems-engineer-salary-SRCH_KO0,21.htm | Lead Embedded System Engineer Contract | 1 |  |  | $470.35/day | $40,450.10 |  |
| https://www.glassdoor.com.au/Salaries/embedded-systems-engineer-salary-SRCH_KO0,25.htm | Embedded System Engineer contract | 3 |  |  | $280.88/day | $68,253.84 |  |
| https://www.glassdoor.com.au/Salaries/lead-machine-learning-engineer-salary-SRCH_KO0,30.htm | Lead Machine Vision Model Engineer contract | 1 |  |  | $520.15/day | 42,132.15 |  |
| https://www.glassdoor.com.au/Salaries/computer-vision-engineer-salary-SRCH_KO0,24.htm | Machine Vision Model Engineer Contract | 4 |  |  | $325.37/day | $105,419.88 |  |
| https://www.glassdoor.com.au/Salaries/team-lead-backend-development-salary-SRCH_KO0,29.htm | Lead Back-End Mobile Application Developer contract | 2 |  |  | $350.85/day | $29,120.55 |  |
| https://www.glassdoor.com.au/Salaries/backend-developer-salary-SRCH_KO0,17.htm | Back-End Mobile Application Developer Contract | 8 |  |  | $315.67/day | $209,604.88 |  |
| https://www.glassdoor.com.au/Salaries/lead-front-end-engineer-salary-SRCH_KO0,23.htm | Lead Front-End Mobile Application Developer Contract | 2 |  |  | $380.16/day | $32,693.76 |  |
| https://www.glassdoor.com.au/Salaries/mobile-applications-developer-salary-SRCH_KO0,29.htm | Front-End Mobile Application Developer Contract | 8 |  |  | $325.07/day | $215,846.48 |  |
| https://www.glassdoor.com.au/Salaries/cyber-security-operations-lead-salary-SRCH_KO0,30.htm | Lead Cyber Operations Contract | 1 |  |  | $460.36/day | $38,209.88 |  |
| https://www.glassdoor.com.au/Salaries/devops-engineer-salary-SRCH_KO0,15.htm | DevOps Contract | 3 |  |  | $360.77/day | $89,831.73 |  |
| https://www.glassdoor.com.au/Salaries/lead-cloud-engineer-salary-SRCH_KO0,19.htm | Lead Cloud Engineer Contract | 1 |  |  | $465.75/day | $15,369.75 |  |
| https://www.glassdoor.com.au/Salaries/cloud-engineer-salary-SRCH_KO0,14.htm | Cloud Engineer Contract | 3 |  |  | $315.07/day | $31,191.93 |  |
| https://www.glassdoor.com.au/Salaries/penetration-tester-salary-SRCH_KO0,18.htm | Pentester Contract | 2 |  |  | $400/day | $8,800 |  |
| https://www.glassdoor.com.au/Salaries/network-team-lead-salary-SRCH_KO0,17.htm | Lead Network Engineer Contract | 1 |  |  | $370.56/day | $18,898.56 |  |
| https://www.seek.com.au/career-advice/role/network-engineer/salary/in-perth | Network Engineer Contract | 3 |  |  | $300.11/day | $45,916.83 |  |
| https://www.glassdoor.com.au/Salaries/qa-tester-salary-SRCH_KO0,9.htm | Quality Assurance Tester Contract | 6 |  |  | $250.08/day | $7,502.40 |  |
| https://www.glassdoor.com.au/Salaries/perth-compliance-officer-salary-SRCH_IL.0,5_IM964_KO6,24.htm | Compliance Officer Contract | 1 |  |  | $300.88/day | $1,805.82 |  |
| https://www.glassdoor.com.au/Salaries/perth-human-resources-salary-SRCH_IL.0,5_IM964_KO6,21.htm | Human Resources (HR) Contract | 2 |  |  | 290.66/day | $57,550.68 |  |
| https://www.glassdoor.com.au/Salaries/risk-officer-salary-SRCH_KO0,12.htm | Risk Officer Contract | 1 |  |  | $300.66/day | $29,765.34 |  |
| https://www.glassdoor.com.au/Salaries/systems-analyst-salary-SRCH_KO0,15.htm | System Analyst Contract | 3 |  |  | $320.53/day | $12,500.67 |  |
| https://www.seek.com.au/career-advice/role/project-manager/salary | Project Manager Salary | 4 |  |  | $2500/day | $1,020,000 |  |
| N/A | Beverages | N/A |  |  | $10/day (per person) | $73,440 |  |
| N/A | Snacks | N/A |  |  | $10/day (per person) | $73,440 |  |
| N/A | Bonuses | N/A |  |  | $750,000 | $750,000 |  |
| Hardware Costs |  |  |  |  |  |  |  |
| Link | Item | Qty. |  |  | Cost per item | Total item costs |  |
| https://www.lenovo.com/au/en/configurator/cto/index.html?bundleId=21RQCTO1WWAU3 | Development Laptop | 44 |  |  | $3,953.03 | $173,933.32 |  |
| https://www.ple.com.au/products/676393/asus-zenbook-a14-ux3407-14-snapdragon-x-elite-16gb1tb-win-11-copilot-ai-notebook | General Laptop | 24 |  |  | $2,399 | $57,576 |  |
| https://aftershockpc.com.au/pc-models/focus-x-machine-learning-ai-workstation?srsltid=AfmBOoq3S2VE_Rbo2o3tPodAAueaB33Sj45jKhVhyE5prRP2-YKKmfvi&step=styling | Machine Learning Desktop | 5 |  |  | 21,999 | $109,995 |  |
| https://www.ple.com.au/products/678148/philips-27e2n1500l-27-qhd-1440p-60hz-ips-monitor | Monitor | 72 |  |  | $169 | $11,999 |  |
| https://www.officeworks.com.au/shop/officeworks/p/j-burrows-4k-60hz-usb-c-to-hdmi-cable-2m-jbuchd4k2m | USB-C to HDMI | 72 |  |  | $35 | $2,520 |  |
| https://www.officeworks.com.au/shop/officeworks/p/logitech-mx-master-4-wireless-mouse-graphite-logi007565 | Mouse | 72 |  |  | $197 | $14,184 |  |
| https://www.bunnings.com.au/antsig-30m-cat6-solid-core-ethernet-network-cable-30m_p0286547?store=2174 | Cat-6 ethernet cable | 10 |  |  | $42.92 | $429.20 |  |
| https://www.scorptec.com.au/product/networking/access-points-&-extenders/104635-u6plus?gad_source=1&gad_campaignid=21687225032&gbraid=0AAAAADsuegMcKQEhy6NB5XuNE09RkqOap&gclid=CjwKCAjwxrLHBhA2EiwAu9EdM3tqC5M3hhGN7SScxeRLq3mjTwRVak4WEgaDLVGyC-Q7lO7MM--OURoCPIwQAvD_BwE | Wireless Access Points | 10 |  |  | $219 | $2,190 |  |
| https://www.ple.com.au/products/672829/ubiquiti-unifi-flex-25g-8-port-25gbe-switch | Network Switch | 1 |  |  | $359 | $359 |  |
| ZED X Stereo Camera |  |  | 1693 | $1,070.85 |  |  | $1,531,019.39 |
| Zed Box (Orin NX 16GB + GPS) |  |  | 1693 | $3133.35 |  |  | $4,774,293.86 |
| Embedded System Cabling |  |  | 1693 | $41.25 |  |  | $59,373.51 |
| https://www.ple.com.au/products/674101/ubiquiti-unifi-dream-router-7 | Router | 1 |  |  | $589 | $589 |  |
| https://www.jbhifi.com.au/products/belkin-6-outlet-surge-protection-strip-with-2m-power-cord | Power Boards (Surge Protected) | 20 |  |  | $45 | $900 |  |
| https://www.jbhifi.com.au/products/hisense-32-a4qau-hd-smart-tv-2025 | TV | 3 |  |  | $295 | $875 |  |
| Software Costs |  |  |  |  |  |  |  |
| Link | Item | Qty. |  |  | Cost per item | Total item costs |  |
| https://visualstudio.microsoft.com/vs/pricing/?tab=paid-subscriptions | Visual Studio Code Professional (Enterprise Standard) | 46 |  |  | $500 / month (per person) | $115,000 |  |
| https://www.flutterflow.io/pricing | FlutterFlow | 20 |  |  | $150 (1st seat)/month $85 (2nd+ seat)/month | $8,825 |  |
| https://github.com/pricing | GitHub | 46 |  |  | $32.19 / month (per person) | $8,047.5 |  |
| https://www.cvat.ai/pricing/cvat-online#team | CVAT | 5 |  |  | $165 / month | $4,125 |  |
| https://www.microsoft.com/en-au/microsoft-teams/compare-microsoft-teams-business-options | Microsoft 365 Business Standard | 72 |  |  | $18.70 / month (per user) | $6,732 |  |
| https://www.notion.com/pricing | Notion | 72 |  |  | $36.79 / month (per user) | $13,244.40 |  |
| https://lucid.app/pricing/lucidchart?km_CPC_AdGroupID=55688908737&utm_source=google&km_CPC_CampaignId=1490375424&km_CPC_MatchType=b&km_CPC_Country=9070554&km_CPC_Keyword=%2Blucidchart+%2Bsubscription&gbraid=0AAAAADLdSjCcYldF3ozdesMkJUDaMTMmp&km_CPC_Creative=442433234546&sessionDate=2025-10-13T06%3A52%3A33.969Z&km_CPC_TargetID=kwd-467383919425&utm_campaign=_chart_en_tier1_mixed_search_brand_phrase_&referer=https%3A%2F%2Fwww.lucidchart.com%2Fpages%2Flanding&gad_source=1&utm_medium=cpc&km_CPC_Device=c&anonId=0.517095ac199dc56750e&gad_campaignid=1490375424&gclid=Cj0KCQjwo63HBhCKARIsAHOHV_XKFLkUMjY31if_uro3z85n-oOwn_AKGysSzIuwWBrPlGeaqPtFFBkaAlZuEALw_wcB&km_CPC_Network=g&sessionId=0.eaa81b41199dc56750f#/pricing/chart | Lucidchart | 72 |  |  | $16 / month (per user) | $5,760 |  |
| https://www.atlassian.com/software/jira/pricing?campaign=19313890769&adgroup=144591249316&targetid=kwd-23471580262&matchtype=e&network=g&device=c&device_model=&creative=689030416734&keyword=jira%20pricing&placement=&target=&ds_eid=700000001558501&ds_e1=GOOGLE&gad_source=1&gad_campaignid=19313890769&gbraid=0AAAAAD_uzhDU8Wgicc8z4-25e5j3YjPvm&gclid=Cj0KCQjwo63HBhCKARIsAHOHV_W0iaiOGgm4AvdpU4Qsehbtg2JkI8rcREU7F0cPtb4wev9G3BSYThEaArwiEALw_wcB | Jira | 72 |  |  | $17/month (per user) | $6,120 |  |
| https://www.adobe.com/au/creativecloud/plans.html | Adobe Creative Cloud Pro | 50 |  |  | $1,895.88/ year (per person) | $94,794 |  |
| https://www.aussiebroadband.com.au/business/internet/nbn-plans/ | Internet Service Provider Plan (Hyperfast Plus) | 1 |  |  | $220/month | $1,100 |  |
| Cloud Costs |  |  |  |  |  |  |  |
| Link | Item | Qty. |  |  | Cost per item | Total item costs |  |
| https://calculator.aws/#/estimate?id=55d57edf8b458517aa7d77920b83369e2c7c55cc | EC2 AWS server | 1 |  |  | $54,337.95 | $54,337.95 |  |
| https://www.mongodb.com/pricing | MongoDB Atlas Cloud Database | 1 |  |  | $2006/month | $10,030 |  |
| Security Costs |  |  |  |  |  |  |  |
| Link | Item | Qty. |  |  | Cost per item | Total item costs |  |
| https://jimssecurity.com.au/product/hikvision-ax-pro-wireless-alarm-package/ | Alarm System + Installation | 1 |  |  | $1395 | $1395 |  |
| https://www.avast.com/business/products/small-business#mac | Avast Premium Business Security | 72 |  |  | $283.85/year (per person) | $20,437.20 |  |
| https://www.accesshardware.com.au/carbine-cel-3in1-sl8snkit-electronic-door-lever-set-satin-nickle | Key-Card Door Lock | 4 |  |  | $313.94 | $1,255.76 |  |
| https://lanyardsfactory.com.au/plain-flat-style-rfid-card | RFID Card | 100 |  |  | $1.79 | $179 |  |
| https://www.bridgetowncomputers.com.au/product/style2/ | CCTV Desktop (High storage) | 1 |  |  | $2495 | $2495 |  |
| https://www.jbhifi.com.au/products/eufy-s3-pro-security-camera-kit-4-pack?ab_version=B&srsltid=AfmBOoqjs6UO7ebtVcBUo89uYde5lLcBIdnqujRVdgUBgs6RItHPz0dacQw | CCTV Camera Kit | 3 |  |  | $1699 | $5,097 |  |
| https://www.jbhifi.com.au/products/eufy-s3-pro-add-on-security-camera | Security Camera | 6 |  |  | $699 | $4194 |  |
| Premises Costs |  |  |  |  |  |  |  |
| Link | Item | Qty. |  |  | Cost per item | Total item costs |  |
| https://www.realcommercial.com.au/short-term-workspace/lucknow-gardens/private-office-space11627 | Office Space | 1 |  |  | $6930/month | $34,650 |  |
| https://www.jbhifi.com.au/products/hisense-hrtf206-205l-top-mount-fridge?store=210&gad_source=1&gad_campaignid=17427148745&gbraid=0AAAAAD23Eqq1F9FtxKWUsM-gl9s6k38HJ&gclid=Cj0KCQjwo63HBhCKARIsAHOHV_WSFhEJJHugqeV0Uk3CRsdZbsWYWaNRYJPD92QynLrooNHaL8JVthQaAmi3EALw_wcB | Fridge | 2 |  |  | $398 | $796 |  |
| https://www.jbhifi.com.au/products/breville-the-barista-express-coffee-machine-liquorice | Coffee machine | 2 |  |  | $699 | $1398 |  |
| https://www.kmart.com.au/product/1.7l-cordless-kettle-41989326/ | Kettle | 2 |  |  | $7.50 | $15 |  |
| https://desky.com.au/products/dual-hardwood-stand-up-desk?variant=39592257716380 | Desk | 40 |  |  | $1,449 | $57,960 |  |
| https://www.eliteofficefurniture.com.au/products/texas-ergo-chair?currency=AUD&variant=45329671356590&utm_source=google&utm_medium=cpc&utm_campaign=Google%20Shopping&stkn=65c244616ea3&gad_source=1&gad_campaignid=19693667750&gbraid=0AAAAACfFuJ93qESV2uKwthkQF40paHbeo&gclid=Cj0KCQjw6bfHBhDNARIsAIGsqLjkTKpP5_510X3EYcR5DNTbnOWcx7gwYr-hO0FaHuuHVODXQZjH3jsaAm9JEALw_wcB | Chair | 40 |  |  | $549 | $21,960 |  |
| https://www.bedbathntable.com.au/ch-eucalyptus-mug-sage-grey-21019401 | Mugs | 20 |  |  | $7.45 | $149 |  |
| https://www.templeandwebster.com.au/Sunnie-19.5cm-Stoneware-Pasta-Bowls-HOTT1182.html | Bowls (Set of 4) | 3 |  |  | $20 | $60 |  |
| https://www.templeandwebster.com.au/24-Piece-Sherwood-Stainless-Steel-Cutlery-Set-2903400-DRMK1441.html?refid=GPAAU447-DRMK1441_200743771&device=c&ptid=&PiID%5B%5D=200743771&utm_content=no_sale&gad_source=1&gad_campaignid=17636172452&gbraid=0AAAAADzVgw36Pa8YU0ZinlVTTj3RRSob6&gclid=Cj0KCQjw6bfHBhDNARIsAIGsqLgSrEcLz88V8yrVs94h92hhHVsB9KX_ZS_1PeqxuRX1xfQhMOs1rGwaAl4wEALw_wcB | Cutlery (Set of 24) | 2 |  |  | $79.99 | $159.98 |  |
| https://www.kogan.com/au/buy/shoifex-kleenex-complete-clean-toilet-paper-60-count-1x60-rolls-packaging-may-vary-j17b09km2pzmh/?utm_source=google&utm_medium=product_listing_ads&gad_source=1&gad_campaignid=21855178544&gbraid=0AAAAADv51P2KKaxtZC5VdGSteZ2i3D3Ww&gclid=Cj0KCQjw6bfHBhDNARIsAIGsqLhFc02U90vL4K2AX2kQakSnbqfoGzP46pIEJLDT6p-sElWw0bzKyLIaAgXREALw_wcB | 60-Pack Toilet Paper (Purchased over 5-month period) | 8 |  |  | $40 | $320 |  |
| https://www.amazon.com.au/VIVA-Paper-Towel-Select-Size/dp/B08BWWWFQ1/ref=asc_df_B08BWWWFQ1/?tag=googleshopdsk-22&linkCode=df0&hvadid=712246395759&hvpos=&hvnetw=g&hvrand=15557694071878811795&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9070547&hvtargid=pla-1656158907066&psc=1&mcid=2f20a9e11e833d699449877332d9c285&tag=googleshopdsk-22&linkCode=df0&hvadid=712246395759&hvpos=&hvnetw=g&hvrand=15557694071878811795&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9070547&hvtargid=pla-1656158907066&psc=1&gad_source=1 | Paper Towels | 5 |  |  | $20 | $100 |  |
| https://www.amazon.com.au/Dettol-Liquid-Raspberry-Pomegranate-Anti-Bacterial/dp/B0BT7Q811H/ref=asc_df_B0BT7Q811H?mcid=c43f653634bb3f2b9dd3edf2ee6c20ae&tag=googleshopdsk-22&linkCode=df0&hvadid=712272868312&hvpos=&hvnetw=g&hvrand=14885100545399346844&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9070547&hvtargid=pla-2009835665265&psc=1&gad_source=1 | 6-Pack Hand Soap | 5 |  |  | $16 | $80 |  |
| https://www.amazon.com.au/Morning-Fresh-Dishwashing-Liquid-liters/dp/B082PMZR29/ref=asc_df_B082PMZR29?mcid=cae8dfa26c8e33b2a9da71fee5357562&tag=googleshopdsk-22&linkCode=df0&hvadid=712246395759&hvpos=&hvnetw=g&hvrand=16288264087758534310&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9070547&hvtargid=pla-890640700739&gad_source=1&th=1 | Dishwashing Liquid | 5 |  |  | $29 | $145 |  |
| https://www.bedbathntable.com.au/osman-turkish-cotton-bale-set-white?gad_source=1&gad_campaignid=20566349252&gbraid=0AAAAADowV5lB69urZ9jR4lQiPBh4XaRsR&gclid=Cj0KCQjw6bfHBhDNARIsAIGsqLhLOpZZbMZEkaeOOLpR3YdtZaHvPwURrT3-bF85gPyLwNbigIYgzXcaArk7EALw_wcB | 8-Pack Hand Towels | 2 |  |  | $59 | $118 |  |
| https://www.thegoodguys.com.au/bosch-series-4-freestanding-dishwasher-black-inox-sms4hvb01a | Dish Washer | 1 |  |  | $999 | $999 |  |
| https://www.amazon.com.au/Finish-Quantum-Dishwashing-Tablets-Lemon/dp/B0F48PC9QN/ref=asc_df_B0F48PC9QN?mcid=a481a1cdcefa37cd8e77aaf4a59e7efe&tag=googleshopdsk-22&linkCode=df0&hvadid=712295732326&hvpos=&hvnetw=g&hvrand=5870169125882094245&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9070547&hvtargid=pla-2426039308050&psc=1&gad_source=1 | Dish Washer Tablets | 10 |  |  | $32 | $320 |  |
| Transportation Costs |  |  |  |  |  |  |  |
| Item |  |  | Qty. | Cost per item |  |  | Total item costs |
| Fuel Card |  |  | 4 | $10,000 |  |  | $40,000 |
| Miscellaneous Costs |  |  |  |  |  |  |  |
| Item |  |  | Qty. | Cost per item |  |  | Total item costs |
| Contingency Reserve |  |  | N/A | $1,432,676.94 |  |  | $1,432,676.94 |

## 3.2. Staff Costs

Bonuses will be awarded to contracted employees which remain committed to the project between the development commencement date and end of contract dates. This is to motivate contracted employees into meeting project deliverables at a high quality whilst remaining part of SSCI-Hooli until project completion. In doing so, employees are unlikely to leave the project midway, reducing the need to use the contingency reserve to contract new employees.

Beverages and snacks are to be provided to employees daily to improve workplace attitudes and maintain employee health. If employees feel their health is prioritised, workplace attitude will increase, producing greater work quality.

## 3.3. Hardware costs

Laptops and machine vision desktops will be purchased rather than rented due to the confidential nature in working with the WA Government in a PPP relationship. By purchasing laptops in a manufacturer state, the project will not be impacted by degraded or old hardware. Finally, it allows IT technicians full control in configuring the systems for optimal team performance. Monitors, mice and USB-C to HDMI cables will also be purchased; these can be sold together with the laptops and desktops after project completion.

The wireless-access points, router, ethernet cables and power boards are required for ensuring all employees can access online software and file storage without delays. In addition, the TVs will be used for increasing team collaboration within meetings.

Stereolab’s cameras, Zed Boxes and cabling are to be fitted into all public transport buses therefore, are required for project success.

## 3.4. Software Costs

All software costs are subscription based, occurring from the 1st January 2026 to 31st May 2026. The listed software are required for the development of documentation, applications, and communication. Adobe Creative Cloud Pro is the exception, requiring a 12-month subscription.

## 3.5. Cloud Costs

The EC2 servers will power the developed applications with the MongoDB cloud database storing pothole data. It is expected to support large traffic frequencies thus, large processing power was considered. These will be rented from Amazon Web Services and MongoDB due to the limited duration of the project.

## 3.6. Premises Costs

The premises will be rented due to the short duration of the project. Office appliances such as, desks and chairs, are to be purchased to ensure acceptable workspaces and comfort. In doing so, work quality is expected to increase. Additional appliances will be purchased for ensuring employee comfort within the workplace, providing additional facilities. In purchasing all appliances within a new state, functionality is expected throughout the project’s duration, eliminating the need for replacements.

## 3.7. Transports Costs

The Field technicians and quality inspector will have access to fuel cards for travelling to fit the hardware within the buses.

## 3.8. Miscellaneous Costs

The large contingency reserve is to be used when listed resources become limited or new resources not listed are required. In addition, it allows for new employees to be contracted in the chance of workflow adjustments or employee departure.

# 4. Assessment of Risk

Projects risks are defined as events which could occur during or after a project’s life which have a negative impact in meeting the set deliverables and/or success criteria.

Risks were assessed on 2 criterias; severity measured how large of an expenditure and regulatory impact the risk would have on the project; likelihood measured the possibility of the risk occurring. Risks will be treated by various employees within SSCI-Hooli, supported by the risk officer. In the occurrence of risks, the risk officer and related risk owner will analyse the current situation, evaluate its short- and long-term impacts, determine solutions and enact a cost-effective countermeasure using the contingency reserve.

## 4.1. Risk Register

| # | Risk | Impact | Category | Severity (1 – 10) | Likelihood (1 – 10) |
| --- | --- | --- | --- | --- | --- |
|  | Employee falls ill with Covid-19 | - Reduced workforce - May spread illness, further reducing workforce | Organisational | 3 | 3 |
|  | Employee falls ill with Influenza (A & B) | - Reduced workforce - May spread illness, further reducing workforce | Organisational | 3 | 4 |
|  | Employee falls ill with Gastro | - Reduced workforce - May spread illness, further reducing workforce | Organisational | 3 | 4 |
|  | Employee gets Rhinovirus | - Reduced workforce - May spread illness, further reducing workforce | Organisational | 3 | 3 |
|  | Employee spreads illness | - Development delays | Organisational | 5 | 6 |
|  | Employee enters maternity leave during project duration | - Spending budget for no project input | Organisational | 4 | 4 |
|  | Field technician receives heatstroke during embedded system installation and faints | - Workers compensation from contingency reserve - Increases workload on other field technicians | Installation issues | 4 | 3 |
|  | Field technician is electrocuted whilst installing embedded system | - Workers compensation from contingency reserve - Increases workload on other field technicians | Installation issues | 7 | 4 |
|  | Hot metal burns Field technician installing embedded system | - Workers compensation from contingency reserve - Increases workload on other field technicians | Installation issues | 5 | 2 |
|  | Field technician slips in heavy rain, dropping and damaging hardware | - New hardware shipment required, increasing costs and delaying bus fitting schedule | Installation issues | 6 | 1 |
|  | Field technician slips in heavy rain whilst installing embedded system getting injured | - Workers compensation from contingency reserve; - Increased workload on other field technicians | Installation | 4 | 1 |
|  | Strong winds push Field technician off bus causing injury and damaging hardware | - Workers compensation allocated from contingency reserve - Increased workload on other field technicians - New hardware required, adding costs and bus fitting delays | Installation issues | 7 | 2 |
|  | Water-filled potholes ignored by vision model | - Potholes remain, increasing in severity | Technical | 8 | 7 |
|  | A lead employee passes away | - Team becomes dysfunctional (missing deadlines, causing scope creep) | Organisational | 8 | 2 |
|  | Project manager passes away | - Project coordination loss - New project manager entering workflow causing disruptions or scope creep | Organisations | 5 | 2 |
|  | All project managers pass away | - Zero project coordination | Organisational | 9 | 2 |
|  | Group lead manages team poorly | - Lack of team synergy - Missing deadlines - Poor work quality | Organisational | 6 | 6 |
|  | All development employees strike for 3 consecutive weeks | - Deadlines unmet - Cascading delays in later tasks - Steering committee consider project managers as disruptions to project success | Organisational | 7 | 3 |
|  | All development employees strike for 3 consecutive days | - Little impact on project meeting final deadline - Steering committee may consider project managers as disruptions to project success | Organisational | 3 | 4 |
|  | Embedded system lead leaves | - Team must adjust to new lead methods - Team receives limited coordination - Task delays may occur | Organisational | 8 | 5 |
|  | Machine model lead engineer leaves mid-way of project completion | - Team must adjust to new lead methods - Team receives limited coordination - Task delays may occur | Organisational | 8 | 5 |
|  | Lead back-end developer leaves | - Team must adjust to new lead methods - Team receives limited coordination - Task delays may occur | Organisational | 8 | 5 |
|  | Back-end development team not listening to cloud engineering team | - Dysfunctional application - Security flaws between back-end and cloud server | Organisational | 8 | 7 |
|  | Cloud engineering team not listening to back-end development team | - Dysfunctional application - Security flaws between back-end and cloud server | Communication | 8 | 7 |
|  | Lead front-end developer leaves | - Team must adjust to new lead methods - Team receives limited coordination - Task delays may occur | Organisational | 8 | 5 |
|  | Lead cybersecurity manager leaves | - Team must adjust to new lead methods - Team receives limited coordination - Task delays may occur | Organisational | 8 | 5 |
|  | Cybersecurity employee creates backdoor to sell to hackers | - Major security flaw created - Contingency funding spent remediating data loss - WA Government distrust in SSCI-Hooli success | Cybersecurity | 9 | 2 |
|  | Lead cloud engineer leaves | - Team must adjust to new lead methods - Team receives limited coordination - Task delays may occur | Organisational | 8 | 5 |
|  | Pentester finds major security flaw and sells the flaw to hackers | - Zero day inside application - Costs remediating flaw after execution | Technical | 9 | 4 |
|  | Pentester finds minor security flaw and sells the flaw to hackers | - Zero day inside application - Costs remediating flaw after execution | Technical | 7 | 4 |
|  | Project manager leaves the project | - Loss of leadership and project direction - Delays as a new manager onboarded | Organisational | 5 | 4 |
|  | Project manager spends budget on personal goods external to project | - Misappropriation of funds and breach of trust - Legal action | Organisational | 10 | 7 |
|  | Compliance officer finds SSCI-Hooli non-compliant, selling information to media | - Public scandal and reputational damage - Potential contract termination | Organisational | 7 | 2 |
|  | Compliance officer finds SSCI-Hooli non-compliant, selling information to competitors | - Confidential data leaked to rivals - Legal implications | Organisational | 6 | 2 |
|  | Developers don't follow system analysis documentation, causing incorrect development | - Software misalignment with client requirements | Organisational | 10 | 6 |
|  | Development teams ignore documentation keeping process, resulting in unkown development progress | - Loss of version control and project visibility - Harder to track progress | Organisational | 9 | 7 |
|  | System documentation is not updated, causing development on already completed source code | - Duplicate work and wasted time - Resource inefficiency and confusion across teams | Organisational | 8 | 5 |
|  | System documentation is incorrectly filled, changing development path | - Incorrect assumptions in further development - Functionality divergence from project goals | Organisational | 10 | 7 |
|  | Source code is not commited to github, causing overlapping workflows | - Multiple conflicting versions created - Integration issues and lost work hours | Organisational | 8 | 5 |
|  | Intern deletes production database 1 month into project duration | - Early-stage data loss - Short-term recovery effort and small data gap | Organisational | 7 | 1 |
|  | Intern deletes production database 4 months into project duration | - Large-scale data loss including processed detections - Major project delays | Organisational | 10 | 1 |
|  | Incorrect github branch is pushed, losing approved source code | - Stable production code overwritten - Project rollback required | Organisational | 9 | 6 |
|  | Authorised employees grant unauthorised entities access to premises | - Breach of physical security - Theft, tampering | Organisational | 6 | 2 |
|  | Development teams are untrained, unable to develop project | - Inability to meet technical requirements - Increased dependence on external consultants | Organisational | 9 | 6 |
|  | Employee uses malicious guide, performing ‘sudo rm-rf’, deleting file system of computer | - Development environment destroyed - Time lost restoring systems and configurations | Technical; Organisational | 6 | 2 |
|  | Employee leaves password on sticky note, granting unauthorised entities system access | - System breach and data exposure - Potential ransomware or privacy violation | Organisational | 6 | 3 |
|  | Different project ideas within a team causing scope creep | - Project direction diverges - Increased workload and cost without added value | Organisational | 8 | 6 |
|  | Development conflicting with project scope | - Deliverables deviate from agreed requirements - Stakeholder dissatisfaction and rework needed | Project management | 9 | 6 |
|  | Employee political view arguments reducing team synergy | - Workplace tension and communication breakdown - Reduced productivity and morale | Organisational | 5 | 4 |
|  | Hardware from Stereolabs is delayed by 1 week, reducing fitting hardware duration times | - Minor schedule adjustment required - Slight compression of testing timeline | Project management | 5 | 4 |
|  | Hardware from Stereolabs is delayed by 1 month, causing employee overtime to occur to meet project duration | - Major delay in integration phase - Increased labour costs and project fatigue | Project management | 8 | 3 |
|  | Hardware is lightly damaged on arrival, causing WA Government to blame damages on SSCI-Hooli (request money back) | - Project budget may be reduced - Trust with WA Government is damaged | Installation issues | 7 | 3 |
|  | Hardware is dead on arrival, requiring new shipment and increasing installation duration | - Project deadline gets extended (project delays) - Additional replacement cost | Installation issues | 7 | 2 |
|  | Hardware cabling arrives damaged, requiring new shipment | - Installation can’t proceed - Additional replacement cost | Installation issues | 6 | 3 |
|  | WA government blames SSCI-Hooli on cable damage, holding project sign-off until remediation | - Project sign-off delay - Reputation damaged | Project management | 8 | 2 |
|  | Embedded system is dropped during installation and broken | - Installation must be repeated - Delays in employment | Installation issues | 7 | 3 |
|  | Embedded system cabling frays, causing a fire | - Can injure personnel - Legal and regulatory consequences | Operations and support | 7 | 3 |
|  | Embedded system overheats within bus and throttles | - Service quality reduced - Potential damage to equipment | Operations and support | 7 | 5 |
|  | Camera is poorly mounted, falling on and killing a child | - Severe legal consequences - Public outrage | Installation issues | 8 | 3 |
|  | Camera is poorly mounted, falling on and encumbering driver, causing a crash | - Traffic accident - Liability claims | Installation issues | 9 | 3 |
|  | Camera is poorly mounted, falling and cracking a lens | - Camera becomes non-functional - Delays in data collection and additional replacement cost | Installation issues | 7 | 4 |
|  | Large pothole detection quantity crashes vision model | - Vision model stops functioning - Delayed reporting, reduced system reliability | Operations and support | 8 | 6 |
|  | Embedded system poorly mounted behind bus instrument panel, triggering airbag | - Airbag accidentally deploys during operation - Risk of injury to driver and passenger, cause legal liability | Installation issues | 7 | 3 |
|  | Condensation causes water build up within embedded system, causing short circuit | - Embedded system failure or power loss - Requires replacement and increased project downtime | Operations and support | 7 | 4 |
|  | Condensation causes water build up within embedded system, causing electrical fire | - Fire hazard endangers passengers - Severe legal, safety and insurance implications | Installation issues | 7 | 4 |
|  | Camera vision blocked by sun glare, reducing pothole detection | - Reduced accuracy of pothole detection - Misleading data collection | Operations and support | 4 | 6 |
|  | Cameras poorly fitted, being stolen by citizens | - Hardware loss - Increased project costs for replacement | Installation issues | 7 | 2 |
|  | Public misinformation on camera use, causing public distrust | - Negative public perception of project | Operations and support | 5 | 4 |
|  | External bus damage from citizen disapproval of cameras | - Bus repair cost and downtime - Stakeholder relations damaged | Operations and support | 3 | 2 |
|  | Project reaches $12M allocation by month 4, unable to be completed | - Project funding exhausted prematurely | Project management | 10 | 6 |
|  | Stereolab hardware increases in cost, requiring contingency cost use | - Reduces available contingency reserves | Project management | 5 | 5 |
|  | Cloud server instances increase in cost, requiring contingency cost use | - Cloud budget exceeded - Other planned upgrades delayed | Project management | 2 | 6 |
|  | Financial penalties from non-compliance of existing state and national laws | - Direct monetary fines and legal costs | Organisational | 5 | 2 |
|  | Accounting errors causing untracked expenditures | - Loss of financial transparency and audit issues | Organisational | 9 | 8 |
|  | Accounting errors causing untracked unspent allowances | - Missed opportunities for enhancements or savings | Organisational | 9 | 8 |
|  | Breaching data privacy through personal data mishandling, causing class action lawsuits | - Legal penalties and compensation payments - Reputation damage | Operations and support; Organisational | 7 | 1 |
|  | Breaching privacy of public citizens through camera monitoring, causing class action lawsuit | - Violation of surveillance laws - Project suspension | Operations and support; Organisational | 7 | 1 |
|  | Legal issues regarding copyright training data in AI models, resulting in legal troubles | - Delays and legal costs incurred | Organisational | 7 | 1 |
|  | WA Government utilising cameras for ulterior motives | - Public backlash and ethical scrutiny | Organisational | 2 | 7 |
|  | Change in road laws disallowing road recording | - Cameras become illegal - Project must be terminated | Project management | 10 | 1 |
|  | Change in road laws disallowing external technology systems in vehicles | - Significant redesign or full project cancellation | Project management | 10 | 1 |
|  | Change in road laws disallowing front window camera mounting | - Cameras must be relocated or removed | Project management | 8 | 1 |
|  | Public protests regarding environmental concerns of embedded system use | - Deployment delays due to community opposition | Users | 3 | 2 |
|  | Scope change – Additional road hazards to be detected, increasing development time | - Increased workload and score creep - Delayed delivery and higher costs | Project management | 6 | 4 |
|  | WA government dissatisfied with tech. demo, holding sign off | - Reputation damage and funding risk | Users | 8 | 5 |
|  | Early sign dashboard too difficult to navigate, limiting use by WA Government | - Addition redesign and training required | Users; Operations and support | 8 | 5 |
|  | Project sign off blocked by weak early dashboard performance | - System considered incomplete - Extended schedule | Project Management | 7 | 5 |
|  | Web map too difficult to navigate, reducing civic reporting participation | - Low engagement from public users - Reduced data accuracy and coverage | Users; Technical | 8 | 5 |
|  | Webmap is slow, reducing civic reporting participation | - Frustrated users abandon platform | Technical; operations and support | 8 | 5 |
|  | Citizen reporting too difficult to perform, reducing civic reporting participation | - Fewer civic inputs | Users; operations and support | 8 | 5 |
|  | Citizen reporting too long to perform, reducing civic reporting participation | - Drop in daily active users | Users; Operations and support | 8 | 5 |
|  | Conflicting project opinions within Steering Committee, reducing alignment of project | - Decision-making delays | Project management | 4 | 3 |
|  | StereoLab embedded system fails to run machine vision model, detecting zero potholes | - System fails to collect data - Project goals not achieved, triggering redesign | Technical | 9 | 4 |
|  | cameras fail to capture high-resolution feed of road conditions, unable to detect potholes | - Poor image input reduces model accuracy - Potholes go undetected | Technical | 9 | 1 |
|  | Vision model falsely detects potholes, wasting remediation expenditures | - Unnecessary road repairs performed - Financial losses and stakeholder frustration | Technical | 7 | 6 |
|  | Vision model reports potholes as false negatives, increasing accident chances | - Dangerous potholes remain unrepaired - Liability for accidents and loss of trust | Technical | 8 | 6 |
|  | Vision model achieving <90% pothole detection accuracy, failing to meet success criteria | - System fails performance benchmarks - Client dissatisfaction | Technical | 10 | 7 |
|  | Vision model achieving <85% early pothole sign accuracy, failing to meet success criteria | - Reduced early detection capability - Increased long-term maintenance costs | Technical | 10 | 7 |
|  | Pothole severity is falsely classified by vision model, increasing urgency to small potholes | - Resources misallocated to minor repairs - Delays in critical pothole repairs | Technical | 5 | 4 |
|  | Pothole severity is falsely classified, reducing urgency to large potholes | - Increased accident probability - Potential injury and legal liability | Machine Vision | 6 | 4 |
|  | Embedded system reports same pothole several times upon detection, increasing cloud traffic | - Increased bandwidth use and cloud cost - Slower data processing | Technical | 4 | 7 |
|  | Embedded system reports same pothole several times upon detection, overloading the web map | - Map performance drops - Public usability reduced and negative feedback | Operations and support | 6 | 7 |
|  | Embedded system reports only one pothole from the many present in camera view | - Incomplete dataset - Reduced model accuracy and credibility | Technical | 8 | 5 |
|  | Incorrect pothole locations within a >1 street difference. | - Misleading maintenance operations | Technical | 9 | 10 |
|  | Web map fails to connect to cloud database and is dysfunctional | - Real-time data unavailable - Reporting and analysis disrupted | Technical | 8 | 3 |
|  | Embedded system fails to create text file of detected pothole information | - Data not uploaded or saved - Loss of detection records | Technical | 8 | 2 |
|  | High web map traffic stopping application functionality | - Platform crash during peak hours - Public frustration and decreased engagement | Technical; Operations and support | 7 | 3 |
|  | Pothole data exceeds cloud database storage limits, requiring contingency reserve use | - Unexpected storage costs - Temporary suspension of data uploads | Technical; Operations and support | 5 | 2 |
|  | Citizen traffic slowing cloud server processes, limiting application functionality | - Web app latency increases - Reduced amount of reports | Technical; Operations and support | 8 | 6 |
|  | Pothole data slowing cloud server processes, limiting application functionality | - Cloud system overloaded - Need for scaling or temporary shutdown | Technical; Operations and support | 8 | 5 |
|  | Automatically detected pothole locations geolocated incorrectly, increasing remediation times | - Misrouted maintenance teams - Increased road hazard exposure | Technical; Operations and support | 9 | 6 |
|  | Embedded systems fail to transmit data via wi-fi, limiting web map to civic reports | - Loss of automated data feed - Reduced detection frequency and accuracy | Technical; Operations and support | 7 | 4 |
|  | Citizen reporting same pothole multiple times to increase awareness | - Duplicate entries inflate pothole statistics | Users | 3 | 9 |
|  | Citizens report non-potholes objects | - False data added to system - Requires additional data filtering | Users | 8 | 10 |
|  | Cloud database corruption deleting detected potholes | - Permanent data lost - Need to restore from backups, causing downtime | Technical | 8 | 4 |
|  | Cloud database deletion, removing all deleted potholes | - Entire data loss - Project setback and data recovery expenses | Organisational | 8 | 3 |
|  | Deletion of machine vision model development branch 4 months into project | - Major data and code loss - Delayed redeployment | Organisational | 10 | 3 |
|  | Deletion of machine vision model development branch 2 months into project | - Model retraining required - Resource reallocation and timeline extension | Organisational | 9 | 3 |
|  | Deletion of mobile application development branch 4 months into project | - Lost progress and user interface features - Project milestone delay | Organisational | 10 | 3 |
|  | Deletion of mobile application development branch 2 months into project | - Partial feature loss - Reduced MVP quality and credibility | Organisational | 9 | 3 |
|  | Deletion of early dashboard development branch application 2 months into project | - Lost reporting functionality | Organisational | 9 | 3 |
|  | Deletion of early dashboard development branch application 4 months into project | - Major component redevelopment - Significant project delays and increased costs | Organisational | 10 | 3 |
|  | Employee selling confidential project data to competitors | - Breach of NDA and confidentiality - Competitive disadvantage and legal exposure | Project management | 7 | 2 |
|  | Employee downloading citizen personal information for monetary gain | - Class action lawsuits and public | Organisational | 7 | 1 |
|  | Development employee creating major security risk to sell to hackers | - System compromised from within - Loss of data integrity and severe trust breach | Organisational | 9 | 2 |
|  | Development employee disclosing major security breach before patch occurs | - Public relation crisis | Organisational | 9 | 4 |
|  | Disgruntled ex-employee deleting project work | - Project progress lost - Recovery time increases and morale drops | Project management | 8 | 3 |
|  | Phishing attack on employees to deploy ransomware | - Project halted until ransom resolution | Technical; Organisational | 8 | 5 |
|  | Malware achieving unauthorised access to cameras | - Privacy violation and live feed exposure | Technical | 3 | 2 |
|  | Malware stopping vision model functionality | - System-wide service outage - Loss of public and client access | Technical; Operations and support | 7 | 4 |
|  | Malware stopping cloud server functionality | - Detection pipeline halted - Downtime and missed data collection | Technical; Operations and support | 9 | 4 |
|  | DDOS attack on cloud server during 8AM to 7PM weekdays | - Service unavailability during critical hours - Government complaints | Technical; Operations and support | 9 | 6 |
|  | Malware manipulating pothole data before entering web map | - False analytics and reports - Misdirected road maintenance spending | Technical; Operations and support | 9 | 4 |
|  | Malware adding false pothole data to web map | - System credibility undermined - Additional resources wasted on fake repairs | Technical; Operations and support | 9 | 4 |
|  | Malware removing pothole data | - Maintenance oversight and data gaps | Technical; Operations and support | 9 | 4 |
|  | Development computers stolen from premises and data extorted | - Confidential data compromised - Financial and reputational losses | Operations and support | 7 | 2 |
|  | Development computers have weak performance reducing development time | - Reduced testing and QA throughput | Technical | 7 | 3 |
|  | Premises damaged by unauthorised individuals, increasing security needs | - Physical asset loss - Costly repairs and downtime | Operations and support | 5 | 2 |
|  | Objects within premises damaged by unauthorised individuals, requiring replacement | - Increases operational costs - Project schedule disruption | Operations and support | 4 | 2 |
|  | Changes to ISO 21448 | - Redesign of validation and testing framework | Project management | 7 | 2 |
|  | Changes to ISO/IEC 27001 & 27017 | - Need for updated policies and audits | Project management | 7 | 2 |
|  | Changes to ISO/IEC 25002 | - Additional testing and documentation | Project management | 7 | 2 |
|  | Changes to ISO 16505 | - Redesign of installation and hardware alignment | Project management | 7 | 2 |
|  | Changes to ISO/IEC 27033-1 & ISO/IEC 27033-2 | - Cost increase in secure infrastructure - Network security architecture must be revised | Project management | 7 | 2 |
|  | Changes to ISO/IEC 23894 | - Model training and documentation updates - New AI risk management standards | Project management | 7 | 2 |

## 4.2. Risk Matrix

SSCI-Hooli believes the following risks are of high severity with a high likelihood of occurrence.

|  | Likelihood |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
|  | 1 |  |  |  |  |  |  |  |  |  |  |
|  | 2 |  |  |  |  |  |  |  |  |  |  |
|  | 3 |  |  |  |  |  |  |  |  |  |  |
|  | 4 |  |  |  |  |  |  |  |  |  |  |
|  | 5 |  |  |  |  |  |  |  |  |  |  |
|  | 6 |  |  |  |  |  |  |  |  |  |  |
|  | 7 |  |  |  |  |  |  |  |  |  |  |
|  | 8 |  |  |  |  |  |  |  |  |  | #114 |
|  | 9 |  |  |  |  |  |  | #36 | #74 |  | #104 |
|  | 10 |  |  |  |  |  |  | #32 |  |  |  |

## 4.3. Risk #32

This risk occurs from one or more of the SSCI-Hooli project managers misusing the $12 million budget for personal expenditures (purchases unrelated to benefitting project success).

Due to SSCI-Hooli incorporating 4 project managers, there is a greater likelihood of incorrect budget use; this can worsen as one project manager views another making personal expenses, choosing to follow. As a result, it was considered with a likelihood of 7. The risk received a 10-severity rating. If the budget was not allocated to the project requirements for success such as, hardware, employees and software procurement would not be possible, resulting in the project remaining at the initiation phase. This would cause the WA Government to receive an incomplete technology driven solution. In addition, the project managers will very likely be sued for the funding misuse, receiving prison sentencing.

To prevent budget misappropriation, SSCI-Hooli will contract 3 accountants to manage the $12 million budget. A lead accountant will own the risk, authorising legitimate business expenses and tracking current budget allocations with the support of the other accountants. An additional mitigation strategy that will be used is the inclusion of 2 project managers for authorisation, ensuring there is a 75% agreement that goods and services to be purchased will benefit project success. In doing so, it ensures the budget is used for achieving the set project deliverables and success criteria. In the case of budget misuse occurring, the lead accountant will seek advice from the risk manager which will be communicated between the 4 project managers and the steering committee.

## 4.4. Risk #36

This involves all development teams within SSCI-Hooli ignoring documentation upkeep. This limits the ability for the WA Government to view the progress of development; this can cascade into the government seeing little progress, pulling funding or not having the ability to upkeep the source code months after project sign off.

In addition, this can cause issues within development. By ignoring documentation, an employee may develop an aspect of the system already created; this will decrease a team’s workflow, increasing the risk of delays. As a result, this risk received a high severity rating. Furthermore, lack of development documentation is very common and easily forgotten, receiving a high likelihood rating.

This risk will be owned by all developers within SSCI-Hooli, enforced by the lead developers of each team. Each week, all teams will undertake a mandatory meeting to perform documentation upkeep; failure to comply would result in salary reductions. This will ensure accountability from each team to maintain consistent documentation, negatively impacting those who choose to ignore it.

## 4.5. Risk #74

This risk occurs from SSCI-Hooli using the provided budget without documenting its destination. This can cause the perception of funds disappearing or increase funding spent on an aspect of the project as it was not documented as previously fulfilled. This risk has a high likelihood of occurrence due to the various teams untracked expenditures can occur from; the team leads may consider expenditure tracking as an afterthought, focusing on meeting the assigned task deadlines. Furthermore, it has a high severity rating as the WA Government may consider these untracked expenditures as stolen budget, seeking legal action against the project managers. Funding will also be pulled as the WA Government no longer trusts SSCI-Hooli to fulfil the project’s deliverables.

This risk will be owned by a lead accountant which will ensure all budget expenditures are documented regardless of transaction size. This will occur by all project managers and lead employees requiring approval from the lead accountant to utilise the budget; this will also ensure the amount requested can occur with the current budget and duration left on the project Finally, the lead accountant will perform monthly checks, ensuring the current budget documentation matches the real budget quantity.

## 4.6. Risk #104

As a pothole is reported by a citizen through voice commands or button inputs within the app, the location is required; there is a high risk of citizens purposely submitting incorrect locations and/or accidentally selecting the wrong location. Careful street selection by citizens is very unlikely to occur as it consumes time; if the citizen app was to confirm locations with multiple button presses, citizens will not utilise the application. This will impact the WA Government and local council pothole remediation efforts as private remediators will be sent to the wrong location, receiving payment for a remediation effort not occurring.

A mitigation strategy is to utilise the geolocation within the current mobile device a report is originating from; this will only require the report be made within a 500m distance of it. The citizen will be allowed to walk away from the pothole location whilst performing the report with the geolocation saved upon the first ‘report’ button press. This will support reporting within autonomous vehicles which will move away from the location of a pothole.

The mitigation of this risk will be owned by the lead front and back-end developers of their respective teams to ensure geolocations can be extracted from the devices at the associated time and processed. This will occur within the assigned development duration and will not impact the completion of the technology driven solution by 31st May 2026.

## 4.7. Risk #114

To report a pothole, citizens will send a photo of the pothole with its location determined automatically. As a result, citizens will have the ability to report false positives; this is caused by the civic app relying on the honesty and trustworthiness of WA citizens, creating an unpredictable risk. By creating an application which may no longer efficiently displays potholes, the project is at a severe risk of not meeting the success criteria; this will cause project failure, with citizens and the WA Government choosing to ignore the use of the technology driven solution.

To mitigate this risk, the machine vision model utilised for automatic pothole detection within the public transport buses will be used, analysing each image transmitted to the cloud. The model will determine the likelihood of the object being a pothole, determining if it is sent for processing or discarded. This risk will be co-owned by the lead vision engineer, back-end developer and cloud engineer due to the risk mitigation requiring the integration of various domains.

# 5. Project Roles

Throughout the project, SSCI-Hooli is expected to consist of 72 employees across diverse teams. Each team will be presented a large goal, with intermediary tasks to be determined by the leads. The development and powering of the applications will be separated into Machine vision, front-end, back-end teams, cloud-infrastructure and networking teams. An accounting team will manage the expenses of the project and a cybersecurity team will protect all SSCI-Hooli digital assets.

SSCI-Hooli will have individual roles such as, pentesters, risk compliance officers, human resources, system analysts and project managers.

| Role | Duration (dd/mm/yy – dd/mm/yy) | Duration | No. in Role | Supervisor |
| --- | --- | --- | --- | --- |
| Removalist | 01/01/26 – 14/01/26 | 9 | Determined by private stakeholder | N/A (External to SSCI-Hooli |
| IT Technician | 15/01/26 – 29/05/26 | 93 | 3 | Project Manager |
| Janitor | 27/01/26 – 29/05/26 | 86 | 2 | Project Manager |
| Lead Accountant | 01/01/26 – 29/05/26 | 99 | 1 | Project Manager |
| Accountant | 01/01/26 – 29/05/26 | 99 | 2 | Lead Accountant |
| Field Technician | 27/01/26 – 20/02/26 27/02/26 – 08/05/26 | 67 | 3 | Quality Inspector |
| Quality Field Inspector | 27/01/26 – 20/02/26 27/02/26 – 08/05/26 | 67 | 1 | Project Manager |
| Lead Embedded System Engineer | 27/01/26 – 29/05/26 | 86 | 1 | Project Manager |
| Embedded System Engineer | 27/01/26 – 22/05/26 | 81 | 3 | Lead Embedded System Engineer |
| Lead Machine Vision Model Engineer | 27/01/26 – 22/05/26 | 81 | 1 | Project Manager |
| Machine Vision Model Engineer | 27/01/26 – 22/05/26 | 81 | 4 | Lead Machine Vision Model Engineer |
| Lead Back-End Mobile Application Developer | 27/01/26 – 27/05/26 | 83 | 2 | Project Manager |
| Back-End Mobile Application Developer | 27/01/26 – 27/05/26 | 83 | 8 | Lead Back-End Mobile Application Developer |
| Lead Front-End Mobile Application Developer | 27/01/26 – 29/05/26 | 86 | 2 | Project Manager |
| Front-End Mobile Application Developer | 27/01/26 – 27/05/26 | 83 | 8 | Front-End Mobile Application Developer |
| Lead Cyber Operations | 27/01/26 – 27/05/26 | 83 | 1 | Project Manager |
| DevOps | 27/01/26 – 27/05/26 | 83 | 3 | Lead Cyber Operations |
| Lead Cloud Engineer | 16/03/26 – 01/05/26 | 33 | 1 | Project Manager |
| Cloud Engineer | 16/03/26 – 01/05/26 | 33 | 3 | Lead Cloud Engineer |
| Pentester | 05/05/26 – 19/05/26 | 11 | 2 | N/A (external to SSCI-Hooli) |
| Lead Network Engineer | 16/03/26 – 27/05/26 | 51 | 1 | Project Manager |
| Network Engineer | 16/03/26 – 27/05/26 | 51 | 3 | Lead Network Engineer |
| Quality Assurance Tester | 13/04/26 – 17/04/26 | 5 | 6 | N/A (external to SSCI-Hooli) |
| Compliance Officer | 05/01/26 – 05/01/26 16/03/26 – 20/03/26 | 6 | 1 | Project Manager |
| Human Resources (HR) | 05/01/26 – 29/05/26 | 99 | 2 | Project Manager |
| Risk Officer | 05/01/26 – 29/05/26 | 99 | 1 | Project Manager |
| System Analyst | 28/01/26 – 13/02/26 | 13 | 3 | Project Manager |
| Project manager | 01/01/26 – 29/05/26 | 102 | 4 | N/A |

## 5.1 Removalists

Removalists will have the role of transporting and furnishing the premises to be used by SSCI-Hooli. It will be outsourced by the project manager role and occur before development phase 1 occurs.

## 5.2. IT Technician

IT technicians will have the role of performing the initial setup of all SSCI-Hooli computer systems, in addition to providing technical support where required. Technical support will occur on an as-needed basis, due to SSCI-Hooli possessing multiple technology backed developers unlikely to require it.

## 5.3. Janitor

Janitors will have the role of maintaining cleanliness and hygiene within the SSCI-Hooli premises. This will occur once daily until the end of project life.

## 5.4. Lead Accountant

The lead accountant will have the role of managing, authorising and delegating expenditures from the $12 million budget. 2 additional accountants will aid this role, assisting in report production and budget tracking.

## 5.5. Accountant

The accountants will have the role of assisting the lead accountant in managing and authorising expenditures from the $12 million budget. The accountants will determine whether a project manager or lead employee’s funding request can be fulfilled, ensuring the budget lasts throughout the project lifetime. Finally, they will ensure all expenditures are documented, mitigating untracked spent or unspent costs.

## 5.6. Field Technician

The field technicians will have the role of installing the stereo cameras, embedded systems and required cabling within the 1,690 public transport buses. They are required to ensure ISO 21448 is followed for maintaining the safety of passengers. The field technicians will be supervised under quality field inspectors to ensure correct fitting.

## 5.7. Quality Field Inspector

The quality field inspectors will have the role of supervising the work done by the field technicians. They are required to check the quality of the stereo camera, embedded system and cabling installations, ensuring it meets ISO 21448.

## 5.8. Lead Embedded System Engineer

The lead embedded system engineer will supervise the 3 embedded system engineers to ensure the systems work as intended. Furthermore, the role must maintain team morale and weekly documentation upkeep. When required, the team lead will produce reports and discuss project progress with the steering committee.

## 5.9. Embedded System Engineer

Embedded system engineers have the role of ensuring the embedded systems correctly send pothole related data to the cloud server with accurate geolocations. In addition, each team member will attend weekly meetings to maintain technical documentation upkeep, allowing discussions of issues which impact embedded system deployment.

## 5.10. Lead Vision Model Engineer

The lead vision model engineer will supervise the 4 additional vision model engineers, ensuring the model meets 90% pothole detection and 85% early sign detection accuracies. Project deadlines involving the model will be enforced by this role, in addition to maintaining team morale. Weekly documentation upkeep is to be enforced by this role. When required the team lead will produce reports and discuss project progress with the steering committee.

## 5.11. Vision Model Engineer

The vision model engineers will have the role of ensuring the vision model achieves 90% pothole detection and 85% early sign detection accuracies within buses. This will occur through efficient data preprocessing, model training, hyperparameter tuning and rigorous testing delegated between the team. When required, the role will involve producing reports for the steering committee and technical documentation upkeep.

## 5.12. Lead Back-End Mobile Application Developer

The Lead Back-End developers will have the role of supervising the development of source code to connect the cloud servers to the front-end of the civic reporting app, web map and early sign dashboard. In addition, the back-end lead will ensure automatically detected potholes by the vision model in buses successfully reaches the cloud infrastructure. In doing so, the leads will communicate with the other lead developers of their respective teams.

The lead back-end developers will co-lead for phase 1 of the application development, splitting into two teams of 5 in phase 2. One team will continue on the back-end development of the civic reporting application and web map, whilst the other team will transfer to development on the early pothole dashboard. Each team will produce separate technical documentation with upkeep enforced weekly.

## 5.13. Back-End Mobile Application Developer

The back-end developers will have the role of producing source code to connect the cloud server to the front-end of the applications and vision model. In doing so, known potholes and early sign data will be displayed with the respective application.

Development will begin as a team of 10, working collaboratively on the civic reporting app, web map and vision model back-end. As development progresses, the team will split into two teams of 5, allowing back-end development of the early sign dashboard to begin, occurring alongside the previous applications.

## 5.14. Lead Front-End Mobile Application Developer

The lead front-end developers will have the role of supervising the development of the civic reporting app, web map and early sign dashboard end-users interact with. In doing so, the leads will communicate with the leads of the back-end teams, ensuring the correct data is displayed to the end-user.

The lead developers will co-lead the 8 front-end developers for phase 1; upon reaching phase 2, each lead will split into a team, supervising 4 other front-end developers. One team will continue development on the civic app and web map, whilst the other begins development on the early pothole dashboard. Each team will produce separate technical documentation, enforced by this role for weekly upkeep.

## 5.15. Front-End Mobile Application Developer

The front-end developers will have the role of producing the civic reporting app, web map and early sign dashboard end-users will interact with. In doing so, they have the responsibility of producing intuitive user-interfaces where pothole reporting can be performed with 2 button presses, a fast-performing web map displaying known potholes and statistic driven dashboard for tracking worsening road conditions.

Development will begin within a single team of 10, working collaboratively to produce the web map and civic reporting functionality. Upon reaching phase 2, the team will split into two teams of 5, with prior development continuing in one team, with the early sign dashboard beginning in another. Both teams will work simultaneously, communicating and sharing resources where required. When required, the teams will communicate with the back-end teams to ensure functionality with the cloud server, in addition to end-users providing feedback.

## 5.16. Lead Cyber Operator

The Lead of Cyber Operations will have the role of ensuring all implemented technologies are secure from cyber-attacks. This is to be performed through rigorous vulnerability testing and technique triangulation to create a multi-layered defence. To do so, the lead will supervise 3 devOps. If vulnerabilities are found by the pentesters they will ensure the cyber team acts to resolve it prior to project completion.

## 5.17. DevOps

DevOps will have the role of digitally securing all digital technology solutions implemented within the project through patching known vulnerabilities and those unique to the project. DevOps will coordinate source code changes with the back-end and front-end teams to implement security techniques whilst supervised by a lead cyber operator.

## 5.18. Lead Cloud Engineer

The lead cloud engineer will have the role of supervising the configuration of the cloud infrastructure. Issues with the cloud services will be forwarded to this role to be remediated within the team.

## 5.19. Cloud Engineer

The cloud engineers will have the role of ensuring the cloud infrastructure can support the storing of pothole data, civic reporting app, web map and early sign dashboard. The cloud engineers must ensure the EWS instances are configured correctly to handle the large traffic frequency each application will produce.

## 5.20. Pentester

The pentester will be outsourced to a business external to SSCI-Hooli, tasked with breaching the digital security implemented by the cyber security team. Vulnerabilities found are to be documented and discussed with the cyber team to produce remediation strategies.

## 5.21. Quality Assurance Tester

The quality assurance testers have the role of rigorously testing the developed applications for software bugs or user-interface choices that negatively impact end-user experiences. Quality assurance testers will communicate with the front-end lead to determine where the applications are weak, providing suggestions from the perspective of an end-user.

## 5.22. Compliance Officer

The compliance officer has the role of ensuring SSCI-Hooli is compliant with project requirements set by the WA Government, in addition to ISO standards, road laws, privacy laws state and nation-wide.

## 5.23. Human Resources (HR)

Human resources have the role of providing communications from stakeholders and the project steering committee towards the relevant lead employee or project manager. In addition, HR will resolve disputes between employees, manage contracts and ensure SSCI-Hooli is maintaining an positive workplace environment.

## 5.24. Risk Officer

The risk officer has the role of identifying possible risks to the project meeting the set deliverables and success criteria, analysing their impacts and developing mitigation strategies. If a risk is of a high likelihood, the risk officer will attempt to support the risk owner in implementing the mitigation strategy.

## 5.25. System Analyst

The system analysts will have the role of creating a development blueprint the front and back-end developers will follow based on the WA Government’s requirements. Throughout the early development lifecycle, the system analysts will re-model and build upon the documentation as they communicate between the development teams on the blueprints current feasibility.

## 5.26. Lead Network Engineer

The lead network engineer will have the role of supervising the 3 additional network engineers in supplying external connectivity to the cloud applications and SSCI-Hooli systems. Network connectivity issues will be forwarded to the lead network engineer who will discuss and remediate the issue with the team. If there are certain connectivity requirements in accessing the early sign dashboard, this role will support SSCI-Hooli in teaching the technology driven solution to the WA Government.

## 5.27. Network Engineer

The network engineers will have the role of connecting all embedded systems and cloud infrastructure to the internet, allowing connectivity to the applications. In addition, the network engineers will maintain the connectivity of all SSCI-Hooli systems. The network team will communicate with the cloud infrastructure team to trouble shoot connectivity issues and test the availability of the applications.

# 6. Professionalism

Through professionalism, SSCI-Hooli aims for high project deliverable quality, in addition to accountability and transparency for the actions taken throughout the project’s life.

Professionalism is required within the development teams to ensure clean and maintainable source code and documentation is developed for the WA government. Each development team will consist of at most five employees; this structure was chosen for increasing collaboration, and team monitoring, whilst minimising miscommunication. The enforcement of GitHub for source code sharing allows all developers access to latest iterations and ability for team leads to review and approve the quality of changes.

Professionalism is also required in managing the $12 million budget. The expenditure document will be continuously revised, ensuring SSCI-Hooli shows accountability and transparency with all expenditures. By utilising 3 accountants, there are fewer sources budget errors can occur from.

Professionalism is vital in the fitting of the physical hardware within public buses. Without it, the WA Government may receive unsatisfactory fitting, leading to risks of meeting the success criteria. Fittings meeting the WA government’s expectations are to occur through following a strict post-installation checklist to be checked by both the field technician and quality field inspector.

Professionalism must be ensured in SSCI-Hooli’s internal and external communications. Employees are expected to communicate exclusively through Microsoft Teams, ensuring a singular communication channel. This ensures messages can be located with ease, preventing critical information loss.

Professionalism will be expected from the project managers and team leads. Each team consists of exactly one lead employee, ensuring the vision of the team can be expressed through a single entity. The use of 4 project managers allows task delegations, providing strong project flow.

Professionalism will be crucial within the pentesting process. Contracted pentesters are to ensure the analysis of SSCI-Hooli’s digital security does not go beyond the terms agreed by the project managers; in doing so, data confidentiality is to be retained. All found vulnerabilities are to also be documented in detail, with steps for reproducibility.

Professionalism will be ensured in the processing of public pothole data. Camera feeds will not be configured for additional tasks beyond automatic pothole detection; this ensures the anonymity of citizens and to limit risks of breaching privacy regulations.

## 6.1. Soft Skills

All SSCI-Hooli employees are expected to possess the following soft skills.

| Skill | Justification |
| --- | --- |
| Communication (Written & Verbal) | Ensures clear, professional internal and external interactions between SSCI-Hooli and stakeholders. Documentation will occur with high quality, transparency and accountability. |
| Problem Solving | Ensures all problems SSCI-Hooli identify are solved efficiently with chosen remediation techniques developed with the project deliverables and budget in conscience. |
| Numeracy | Ensures all employees can perform basic cost calculations and create statistical graphs within their respective role. |
| Computer literacy | All employees will require basic computer skills, capable of web searching and Office365 use. |
| Critical thinking | Ensures all project choices are determined for ensuring a high quality of project success. |
| Teamwork | Ensures all employees can work effectively with others to complete tasks using diverse viewpoints and backgrounds. |
| Compromisation | Ensures an employee can settle for the use of multiple solutions beyond their own. |
| Active Listening | Ensures actions are taken after clear project understanding is developed. |
| Conflict resolution | Ensures employees can resolve disputes to maintain group morale and task output. |
| Initiative | Encourages employees to be proactive, identifying improvements, tasks and risks; acting upon it without order from the team lead. |
| Flexibility | Ensures adaptability to new technologies and software, in addition to changing group dynamics and tasks. |
| Organisation (Time & Self) | Ensures employees can prioritise tasks, meet deadlines and manage documentations professionally. |
| Leadership | Ensures leads can achieve a high performance from teams through consistent progress and quality assurance. |
| Attention to Detail | Employees must possess this skill to achieve a high delivery quality in source code, documentation and steering committee reports. |

## 6.2. Hard Skills

The following hard skills are expected from SSCI-Hooli employees dependent on the role attained.

| Skill | Justification |
| --- | --- |
| Programming Proficiency | Ensures all developers are capable in writing professional and efficient source code within their respective programming language. |
| System Analyst Proficiency | Supports the design and optimisation of system architecture, ensuring integration between hardware, software, and cloud components with the WA Government’s vision. |
| Accounting Proficiency | Ensures transparent budget tracking and cost allocation, meeting professional documentation requirements. |
| Machine Vision Proficiency | Required for the development of the vision model for automatic pothole and early sign detection model. |
| Vehicle Maintenance Proficiency | Required for installing and maintaining the physical hardware used for automatic pothole detection. |
| IT Support Proficiency | Provides support for computer issues impacting employee workflows, in addition to performing modifications requested by employees without authorisation. |
| Embedded System Proficiency | Ensures proper configuration and testing of embedded systems and associating hardware used in automatic pothole detection. |
| UI/UX Proficiency | Ensures an intuitive and friendly user interface is implemented within all applications accessible to end-users. |
| Back-end Architecture Proficiency | Supports the design and maintenance of scalable APIs and databases, enabling reliable data transmission between devices and cloud services |
| Cloud Infrastructure Proficiency | Ensures effective use of cloud instances for secure and fast application use. |
| Penetration Testing Proficiency | Used to identify vulnerabilities within the technology driven solution. |
| Network Development & Maintenance Proficiency | Required to allow external connectivity to the cloud applications and pothole data delivery. |
| Data Analytics Proficiency | Used within SSCI-Hooli to analyse team and developing application performances |
| Cybersecurity Proficiency | Required to protect citizens from cyberattacks which impact application accessibility and data integrity. |

## 6.3. Ethics

All employees of SSCI-Hooli are required to follow the ACS code of ethics to ensure a positive workplace environment and professional source code and documentation development.

## 6.4. Government and Corporate Communications

Communication between SSCI-Hooli and the WA Government will primarily occur within the weekly steering committee meetings with concerns and queries addressed to the present project managers. Additional stakeholders will communicate with the project managers which will then forward requests or queries to the appropriate team lead. Online communication is expected to occur through the approved channels, with all outgoing written documentation to follow a high level of professionalism, transparency and accountability.